## LOC Events To-Do
The following document is General Checklist for hosting a Skate Ontario event. In an effort to support all Host Clubs, a comprehensive list of "to-do's" has been complied to assist in the planning and execution of your event. Each event is unique and not all items listed may pertain to your event, and timelines may look different. Use the following as a guide to aid in your planning and event execution. Your SOSPOC and the entire Skate Ontario Events Team is here to support and assist throughout the process. If you have any questions or recommendations to the following document, please reach out to your SOSPOC or events@skateontario.org
Pre-Event Planning (Post Contract Signing & Ongoing)
Book & Secure Ice Contract & any necessary rooms/space required
Recruit Local Organizing Committee (Chair, Treasurer, Registration, Volunteer, Logistics, Awards, Hospitality, etc.)
Meet with Facility to confirm if they have any needs/requirements (it is best to have this early on so there are no surprises) - Setup Requirements/Restrictions - Officials Stands - Glass Removal
Type of sound system in the arena. Where connections to the sound system are located? What sound equipment is required? Are there are any restrictions on installing additional equipment to support the event?
Confirm table & chair availablility from Facility
Confirm & Book any rental equipment needs: - Narrow judge tables - Cushioned chairs for Judges Stand - Tables (if not supplied by Facility) - Chairs (if not supplied by Facility) - Pipe & drape - Music equipment - Linens - Radios - Printer or Photocopier (confirm with DS Lead on requirements)
Decide how Officials Stand will be Constructed: Volunteer Built, Rented, Faclity Constructed (Official Stands Optional for STAR 1-4 Events) Confirm supplies required, length of the stand, drawings (if required), etc.
Decide how meals to be managed: Volunteer, Catered, Facility Catered
Create Sponsorship Letter/Package & approach Local Businesses for sponsorship dollars or in-kind items: Examples: Meals/Snacks, Rental Equipment, Awards Decorations, Stationary Needs, Music Equipment, Radios, Pipe & Drape, Table Linens, Tables/Chairs, Skater Goodie Bags, Officials Gifts, Raffle/Door Prize, etc.
Decide where Awards Podium will come from - Options: build/rent/borrow from other club
Decide if you want to host Practice Ice (For Sectional/Provincial/Synchro events)
Book & Secure Photographer (optional)
Decide if you want to have Skater Goodie Bags (optional, LOC expense)
Decide what Skater Accreditation will look like (optional, LOC expense)
Decide Location of the Following Items:
Registration Space (Skater/Coach/Music Registration)
Warm-up Areas
Officials Room
Data Specialists Room
Hospitality Room (Where Officials will eat their Meals - Depending on space this could be in the Officials Room)
Music and Announcing Location
On and Off Ice Door
Videographer Location
Where glass should be removed to facilitate coach/athlete interaction and for videographer (If Required)
Medical Room
Vendor Location(s)
Results Posting (STAR 1-4 Only)
STAR 1-4 ONLY
Set Event Budget
Book & Secure Hotel Rooms for Officials - All rooms should have 2 beds
Book & Secure Videographer (optional)
Book & Secure Medical
Decide how Officials Expenses will be paid - On-site, Mailed Post Event, etc. (Ask SOSPOC for blank Skate Ontario expense form if needed)
12 Weeks Out
Send SOSPOC information to include in Annoucement Examples: Admission Pricing, Practice Ice information, etc.
10 Weeks Out
Event Announcement posted by Skate Ontario
8 Weeks Out
1st OC Meeting - arranged by SOSPOC This meeting is meant for everyone to meet each other and discuss needs/requirements. Refer to Work Plan for Agenda Items
Confirm the length of Officials Stand required by DS Lead and ensure plans accommodate for this.
Confirm with Tech Rep Number of Hotel Rooms Needed for Officials (STAR 1-4 Only)
Starting 8 Weeks Out (ongoing)
Start recruiting volunteers and filling out volunteer schedule
Determine menu for meals, including snacks
Determine where breakfast will be served - Hotel/Arena/Responsible for their own breakfast and can expense
Call for vendors (Optional) Examples: Flower Sales, Skating Apparel, Local Businesses, etc.
Setup & Test Music and Announcing to identify any potential issues. Use exact system that will be used at the event.
Be available and on-site to facilitate the internet install and be prepared to run a speed test (Only if the event is being Livestreamed)
Submit for Event Insurance through BLF Canada (STAR 1-4 Only)
Decide on Officials Gift - Suggested value: $20/day (STAR 1-4 Only)
4 Weeks Out
Order medals & ribbons from Nothers - Work with your SOSPOC to determine how many you should order
Gather Skater Accrediation Supplies
Gather stationary supplies required for DS Team & Volunteer Positions (can be done over the next 4 weeks)
3 Weeks Out
Schedule Posted on the Website
Create Dressing Room Schedule - By club/by category. Need to account for Male & Universal Dressing room depending on number of available dressing rooms
Create Awards Schedule - Options: On the hour, 15-30 minutes after the group finishes, or other alternative that what works best for you
Create Signage: Wayfinding, Dressing Rooms Assignments, Admission Pricing, Medal Ceremony Schedule. For Sectional/Provincial/Synchro Series events, SOSPOC will bring some signage. Confirm with your SOSPOC on the equipment.
Send hotel rooming list/cancel rooms. This date will very based on your agreement with the hotel. (STAR 1-4 Only)
2 Weeks Out
2nd OC Meeting - arranged by SOSPOC This meeting is meant to confirm that everything is in place and we are good to go! Refer to Work Plan for Agenda Items
Confirm any Dietary requirements
Share schedule & flood schedule with the facility
Send SOSPOC information to be included in Athlete Email sent week of event Examples: On-site vendors, Specific venue instructions (Parking, Warm-up areas), etc.
Medals & Ribbons received - Highly recommended that box is opened and confirmed correct medals are received
Finalize that all plans are in place for a successful Officials Stands setup
Week of the Event
Pick up all the event rentals
Have all printed items ready (ie. signage, schedule)
Ensure volunteers are aware of their schedules
Gather hospitality supplies & items
On-Site Setup - Day Prior or Day of
Provide meal during set-up for volunteers and Officials on-site (Determined in advance if required)
Removal of glass by Facility (if required)
Officials Stands, including setup of Tables & Chairs Anchor Officials Tables to the Officials Stand or kick plate at front of stand
Setup & Test Music and Announcing
Setup Officials Room & DS Room (if in different location) - Tables & Chairs
Setup Printer/Copier (if required) & supplies in DS Room
Setup Skater & Music Registration Tables
Setup Admission Tables - Post Admission Prices,
Setup Hospitality Room - Arrange room, setup non-pershiable items
Setup Medal Ceremony Podium
Setup chairs at security "checkpoints" - where admission checks will be & by skater only areas (ie. dressing rooms)
Setup wayfinding signage
Post Dressing Room Assignments on Dressing Room doors & at Skater Registration
Post Schedules around the Facility (Specifically at Admission Tables, Dressing Rooms, by Skater on Door)
Post Medal Ceremony Schedule or Signage of when they will take place
Organize medals
Setup Tables & Chairs or desginated area for vendors
On-Site During the Event
Skaters begin arriving 1 hour prior to event start
Ensure all volunteers check-in on arrival and briefed on their role
Admissions setup & operational
Hospitality - Setup/snacks & meals replenished
Confirm Medical is on-site (STAR 1-4 only, SOSPOC will look after for all other events)
Check on volunteers at least hourly and provide breaks to eat/warmup
Check on Admissions to ensure they have enough change/clear out extra cash
Post Event
Pay any outstanding invoices
Pay Entandem Fees (STAR 1-4 Events only)
Submit post event report to Skate Ontario
Items Needed for Volunteer Roles
Admissions
Wristbands or Stamp to mark hands
Cash Float
Sign with pricing for admission
Event Schedule
Awards Schedule
Skater Registration & Music Registration
Event Schedules for Posting
Music - Sign in/sign out sheet OR Start Orders
Start Orders for Skater Registration (Provided by DS Team)
Coach Sign-In (Provided by SOSPOC)
Pens/Highlighters
Dressing Room Schedule
Awards Schedule
Dressing Room - Optionals
Clipboard with:
Dressing Room Schedule
Event Schedule
Start Orders (Provided by DS)
Pen/Highlighter
Ice Captain
Clipboard with:
Dressing Room Schedule
Event Schedule
Start Orders (Provided by DS)
Pen/Highlighter
Music & Annoucing
Music Playing Equipment
Microphone
Batteries if wireless microphone
Announcing Scripts
Stop Watch (To time warm-ups. Can use a phone if no stop watch is available)
Selection of Warm-up music
Series 8 Dance Music
If STAR 1 or Creative Improv is being offered (music for this)
Clipboard with:
Pen
Start Orders & Officials (Provided by DS)
Warm-up Times
Event Schedule
Warm Up Area - Synchro
Clipboard with:
Warm-up Schedule
Event Schedule
Guard Runners - Synchro
Table near off-door to put skate guards on
Box/bin to put skate guards in (ie. wine box/milk crate/grocery bin)
DS Supplies
Refer to list included in Appendix B